## Sheet1
Ann Arbor Timeline
|  | Start Date | Complete Date | Duration (Days)
City Approvals
Option Agreement / Execution
| DDA Parking Agreement | 2009-05-01 | 2009-05-31 | 30
| Commmunity Engagement Plan | Complete
| DDA Approval of Parking Design | 2009-01-15 | ?
Option Extension through December 09 |  | 2009-04-15 | 2009-04-25 | 10
PUD
| 1st Planning Review | Complete.
| Update Drawings | Complete.
| Complete Supplemental Regs | Complete.
| Submit Updated PUD Drawings | Complete.
| Planning Publication | Complete.
| Submits to City Council | Complete.
| Council Approval | Complete.
Staging Plan
| Lease Hodesh Space | Complete.
| Submit Staging Plan | Complete. | 2009-09-16
Financial Approvals
| Preliminary Board Package | Complete.
| Equity Partner Review | 2009-02-02 | 2009-05-15 | 102
| Equity Commitment Letter | 2009-02-02 | 2009-06-15 | 133
| Construction Lender Review | 2009-02-02 | 2009-05-15 | 102
| Construction Commitment Letter | 2009-02-02 | 2009-06-15 | 133
Building Permit
| Engineering Approval | 2009-08-14 | 2009-09-03 | 20
| First Building Permit Plan Check | 2009-09-14 | 2009-10-29 | 45
| 2nd Plan Check | 2009-11-09 | 2009-12-15 | 36
| Permits Issued |  | 2009-12-15
Architectural Design
| SD Approval | Complete.
| SD Cost Estimate | Complete.
| DD Document Prep | 2009-01-01 | 2009-05-15 | 134
| DD Review | 2009-05-15 | 2009-06-15 | 31
| DD VE and Approval | 2009-06-15 | 2009-07-01 | 16
| CD Document Prep | 2009-06-15 | 2009-09-15 | 92
| CD 85% Complete | 2009-09-15 | 2009-09-15 | 0
| CD VE Meetings | 2009-09-15 | 2009-10-01 | 16
| Update Drawing Permit Set | 2009-10-01 | 2009-10-15 | 14
| Contract Negotiation | 2009-10-15 | 2009-12-15 | 61
| Award Construction Contract | 2009-10-01 | 2009-12-15 | 75
Final Board Package
| Final Budget / Plan | 2009-09-15 | 2009-10-15 | 30
| Final Insurance Review | 2009-10-15 | 2009-10-27 | 12
| Final Proforma | 2009-09-16 | 2009-10-15 | 29
| Equity Partnership Agreement | 2009-06-15 | 2009-10-13 | 120
| Equity Inspecting Architect Contract | 2009-10-13 | 2009-11-27 | 45
| 85% CD for Appraisal | 2009-09-15 | 2009-09-15 | 0
| Contruction Contract Signed | 2009-10-01 | 2009-11-16 | 46
| Construction Loan Documents | 2009-09-01 | 2009-12-15 | 105
| Construction Loan Closing | 2009-12-11 | 2009-12-15 | 4
Steps to Issue Bonds
Review of Title, Order Title Work,
Bond Due Diligence, Publish Intent to Issue
City Drafts Statement, request rating, adopts resolution, and mails stmnt.
End of 45-day referendum period
Preliminary Official Statement Mailed
Preliminary Pricing of Bonds
City Adopts Sale Resolution
Bond Purchase Agreement Signed by City
| Closing of Bonds |  | 2009-12-15
Affordable Housing
| Document reviewed by Developer and City |  |  | 30
| Overall Master Deed Approval and Review |  |  | 60
Finalization of Condo Documents
| Recording of Master Deed |  |  | 60
Construction Schedule
| Closing | 2009-12-14 | 2009-12-15 | 1
| Mobilization, Site Utilities and Foundation | 2009-12-15 | 2010-09-10 | 269
| Parking deck substatnial completetion | 2010-09-10 | 2011-01-03 | 115
| First Floor Cert. Substantial Completion | 2011-01-03 | 2011-02-22 | 50
| Second Floor Cert. Substantial Completion | 2011-02-22 | 2011-03-15 | 21
| Third Floor Cert. Substantial Completion | 2011-03-15 | 2011-04-01 | 17
| Fourth Floor Cert. Substantial Completion | 2011-04-01 | 2011-04-22 | 21
| Fifth Floor Cert. Substantial Completion | 2011-04-22 | 2011-05-11 | 19
| Sixth Floor Cert. Substantial Completion | 2011-05-11 | 2011-05-16 | 5
| Completion | 2011-05-16 | 2011-05-25 | 9
526
Marketing
| Marketing Materials | 2010-11-26 | 2011-02-24 | 90
| Pre-Pre Leasing | 2010-12-26 | 2011-02-22 | 58
| Pre Leasing | 2010-10-25 | 2011-02-22 | 120
| Model | 2011-02-22 | 2011-02-22 | 0
| First Resident Move-In |  | 2011-02-22
Formulas:
Complete Date = [Start Date]+[Duration (Days)]
Complete Date = [Start Date]+21-1
Start Date = [Start Date, row above]
Start Date = [Complete Date, row above]+11