## AUG2020 WORK SESSION
Action item number | Date created | Full Commission? Or Working Group? | Task Description | A2Zero Actions supported | A2Zero Prioritization (matrix) rank (the lower the number, the higher the priority) | Questions: | Comments | Members | Owner/Lead | Target completion date | Status
1 |  | Full commission | Supporting development of the A2Zero opportunity assessment for: (a) homeowners; (b) Renters; (c) Businesses; and (d) Visitors | most strategies and actions | NA but due to breadth, likely high | a. Is the task to help create the assessments or to provide input on draft assessments developed by OSI (and/or others)? b. Is this envisioned as something like a carbon footprint tool where a review of one’s lifestyle and built environment generates opportunities to reduce one’s footprint? c. Is it foreseen as a self-assessment or to be done with external support, e.g. concierge service or trained volunteers? d. Should this be assigned to the Community Outreach Working Group?
2 |  |  | Invite speaker from AAPS to share sustainability plans | [5 empty] | C. Colvin-Garcia | October 2019 | Completed
2 |  | Full commission | Continue to monitor and support state and federal clean energy legislation | Action 1-1, Community Choice Aggregation Action 1-2, Onsite Renewable Energy Generation Action 1-3, Community Solar Program Action 3-2, Update Building Codes (e.g. ZERO Code) Action 7-3, Carbon Price (federal legislation, not A2-internal) | NA but due to breadth, likely high | a. Does the task include drafting and approving resolutions of support? b. How does this differ / go beyond the City’s lobbying agenda? c. Would this involve coordination and collaboration with the Ann Arbor Climate Partnership (A2CP), its members and its member organizations?
3 |  | Full commission | Support the Annual A2Zero Summit | most to all | NA but likely moderately high | a. Should this be assigned to the Community Outreach Working Group? b. What would this entail? Input on the agenda, identifying presenters? Commissioner presentations? Volunteering at the event?
5 |  |  | Solicit potential conflicts of interest from Energy Commissioners | [5 empty] | J. MacDonald | September 2019 | Completed
6 |  |  | Solicit Commissioner interest and commitments for 2020 subcommittees | [5 empty] | S. Lenski | September 2019 | Completed
7 |  |  | Determine if dial-in phone option is available for Commissioners to participate in EC meetings if they cannot be in person | [5 empty] | J. MacDonald | September 2019 | Completed
8 |  |  | Share GHG inventory analysis with Commissioners as a pre-read | [5 empty] | J. MacDonald | September 2019 | Completed
9 |  |  | Send information to Commissioners about volunteerism for fire station solar installation | [5 empty] | J. MacDonald | September 2019 | Completed
4 |  | Full commission | Contribute to the design of the energy concierge program | Action 3-6, Energy Concierge and Community Education | 42 |  | The prioritization ranks seems extremely low given the concierge program will be a go-to source for technical, financial, vendor and other information for many other Actions and programs
5 |  | Full commission | Provide input into the A2Zero Youth and Neighborhood Ambassadors program | Action 6-2 and many others | 6 | a. Should this be assigned to the Community Outreach Working Group? b. Is the task to help create the program or to simply provide input on a draft program description developed by OSI (and its consultants)?
12 |  |  | Circulate updated, proposed bylaw "purpose and duties" language with Commissioners to prepare language for a vote | [5 empty] | S. Lenski | 9/27/2019 | Completed
6 |  | Full commission | Provide input into and help advertise the annual A2Zero survey | most / all | NA | Should this be assigned to the Community Outreach Working Group?
7 |  | Full commission | Support public engagement and outreach |  |  | Should this be assigned to the Community Outreach Working Group?
8 |  |  | Share legal feedback on solar access whitepaper | [5 empty] | J. MacDonald | December 2020 | Completed
9 |  |  | Share input on carbon neutrality / Town Hall / TAG | [5 empty] | J. MacDonald / M. Stults | December 2020 | Completed
10 |  |  | Share metrics on solar installs in A2 | [5 empty] | J. MacDonald | February 2020 | Completed
8 | 2018-07-01 | Transportation Electrification Working Group | Support getting the EV-readiness Ordinance over the finish line | Action 2-6 | 12 | The Working Group has two open tasks, as decided in its August 4 group meeting: a. Develop an Energy Commission resolution in support of the EV-readiness Ordinance for a first reading at the August 11 Energy Commission working session and for vote at the September 8 commission meeting b. Finalize an EV Charging Guide for Developers with a due date TBD |  | Commissioners Colvin-Garcia, Hookham, Mirsky and Zocher; resident volunteers Appleyard, Chen, Gordon, Griffith, Stefanopoulou; staff liaison Simi Barr |  | October 2021
9 |  | Transportation Electrification Working Group | Support development of a comprehensive EV strategy | Action 2-2, Bus Electrification Action 2-3, Bulk Purchase EVs (and Storage) Action 2-4, Electrify City EV Fleet Action 2-5, Electrify Private Fleets Action 2-6, Expansion of Electric Vehicle Charging Infrastructure | Action 2-2, Bus Electrification: 36 Action 2-3, Bulk Purchase EVs (and Storage): 2 Action 2-4, Electrify City EV Fleet: 21 Action 2-5, Electrify Private Fleets: 31 Action 2-6, Expansion of Electric Vehicle Charging Infrastructure: 12 |  | See Emily Drennen / Charles Griffith strategy paper | Commissioners Colvin-Garcia, Hookham, Mirsky and Zocher; resident volunteers Appleyard, Chen, Gordon, Griffith, Stefanopoulou; staff liaison Simi Barr
10 |  | Transportation Electrification Working Group | Support staff in creation of an EV bulk buy program (including ebikes) | Action 2-3, Support Community Electric Vehicle (and Solar) Bulk Buys Action 4-1, Implement Non-Motorized Transportation Plan | Action 2-3, Support Community Electric Vehicle (and Solar) Bulk Buys: 2 Action 4-1, Implement Non-Motorized Transportation Plan: 11 |  |  | Commissioners Colvin-Garcia, Hookham, Mirsky and Zocher; resident volunteers Appleyard, Chen, Gordon, Griffith, Stefanopoulou; staff liaison Simi Barr
11 |  | Transportation Electrification Working Group | Public EV Education for: (a) Individuals; and (b) Large Businesses |  |  | Split into two groups, one for Individuals and the other for Large Businesses? |  | Commissioners Colvin-Garcia, Hookham, Mirsky and Zocher; resident volunteers Appleyard, Chen, Gordon, Griffith, Stefanopoulou; staff liaison Simi Barr
15 |  |  | Office of Sustainability and Innovation provide update on progess over last 6 months | [5 empty] | J. MacDonald / M. Stults | January 2020 | Completed
12 |  | Housing and the Built Environment Working Group | Contribute to community benchmarking and transparency Work |  |  |  | Work with 2030 District on their work in the commercial sector along with energy disclosers more broadly |  | C. Hookam | tbd
13 | ?? | Housing and the Built Environment Working Group | Support completion of Time of Marketing ordinance |  |  |  | Along with multifamily and the commercial sector. Join with the above point | Commissioners Mirsky, Macomber, Hookham (and others to a limited degree); resident volunteer Appleyard; staff liaison Josh MacDonald and Thea Yagerlener (double check) | J. Mirsky | February 2020
14 |  | Housing and the Built Environment Working Group | Support development of green rental housing program
15 |  | Housing and the Built Environment Working Group | Support development of electrification, energy efficiency, and distributed generation pilot |  |  |  | Financing element as well
16 |  | Renewables Working Group | Support State of Michigan Community Choice Aggregation (CCA)-enabling legislation | Action 1-1 | 3 |  | check for legislation status update
17 |  | Renewables Working Group | Support Onsite RE Generation with Battery Storage (Bulk Buys) | Action 1-2 | 6 |  | Building off of Julie's Roth Solarize program
18 |  | Renewables Working Group | Support the State of Michigan Community Solar (CS)-enabling legislation and then promote | Action 1-3 | 21 | How is this different that Action 2-3? | check for legislation status update
19 |  | Renewables Working Group | Support the Landfill Solar Project | Action 1-4 | 31
20 |  | Renewables Working Group | Support Community (Electric Vehicle and) Solar Bulk Buys | Action 2-3 | 2 | How is this different than Action 1-3? Combine with above
21 |  | Community Outreach Working Group – Combine with Outreach to Schools Working Group? | Support the Annual A2Zero Summit |  |  | Already above | This is also an OSI recommendation for the full Energy Commission (see above)
22 |  | Community Outreach Working Group – Combine with Outreach to Schools Working Group? | Provide input into the A2Zero Youth and Neighborhood Ambassadors program |  |  | Already above | This is also an OSI recommendation for the full Energy Commission (see above)
23 |  | Community Outreach Working Group – Combine with Outreach to Schools Working Group? | Provide input into and help advertise the annual A2Zero survey |  |  | Already above | This is also an OSI recommendation for the full Energy Commission (see above)
24 |  | Community Outreach Working Group – Combine with Outreach to Schools Working Group? | Public EV Education for: (a) Individuals; and (b) Large businesses |  |  | Already above | This is alson an OSI recommendation for the Transportation Electrification Group (see aboveC)
25 |  | Outreach to Schools Group – Combine with Community Outreach Working Group? |  |  |  |  | Commissioners talk on Ann Arbor Public Schools Comments section. Get Lauzzano to present to energy commission regularly
26 |  | 100% Clean and Renewable Municipal Operations | Support the Landfill Solar Project |  |  | Change to solar on municipal buildings. Energy Efficiency. Talk to unions with Robert and Mark | This is also a Renewables Working Group project (see above)
27 |  | 100% Clean and Renewable Municipal Operations | Support development of a comprehensive EV strategy |  |  |  | This is also a Transportation Electrification Working Group project (see above)
28 |  | 100% Clean and Renewable Municipal Operations | Electrify all municipal HVAC systems (e.g. geothermal or air-to-air / VRF heat pumps) | Action 2-1 | 17 but only a small fraction of the total impact
29 |  | Funding - Jay
30 |  | Looking for minority representation on commission - equity Clevey
31 |  | Michigan Saves revolving funds for low income communities