## A2 Schedule
Ann Arbor City Apartments Estimated Timeline
Updated: 7/29/10 (corrected)
|  |  |  | City's | City's | Duration
|  | Start Date | Complete Date | Start | Completion Date | (Days) | Notes
City Approvals
Option Agreement / Execution |  | extended thru 8/5/2010
Commmunity Engagement Plan |  | Completed 10/2/2007
DDA Parking Garage
| DDA Parking Agreement | Completed 10/3/2007
| DDA Parking Agreement Amendment No. 1 | Completed 4/7/2008
| DDA Approval of Parking Design | Completed 5/8/2009
| Parking Agreement Amendment No.2 Draft by City Attorney | 2010-08-05 | 2010-08-26 |  |  | 21
| Documents reviewed/completed By Developer and City | 2010-08-26 | 2010-09-29 |  |  | 34
| DDA Attorney Reviews Draft Parking Agreement/Proposes Edits | 2010-09-20 | 2010-09-29 |  |  | 9
| DDA Operations Committee Review of Parking Agreement Amendment No. 2 | 2010-09-29 | 2010-09-29 |  |  | 0
| Developer and City Respond to DDA Operations Committee Review Comments | 2010-09-29 | 2010-10-01 |  |  | 1
| DDA Board Reviews Draft Parking Agreement Amendment No. 2 | 2010-10-06 | 2010-10-06 |  |  | 0
| Developer/City/DDA Attorneys Document review/completed | 2010-10-06 | 2010-10-13 |  |  | 7
| DDA Puts Forward Recommended Agreement for Board Approval | 2010-10-27 | 2010-10-27 |  |  | 0
| DDA Votes to Approve Parking Agreement Amendment No. 2 | 2010-11-03 | 2010-11-03 |  |  | 0
| City Council Approval of Parking Agreement Amendment No. 2 | 2010-09-29 | 2010-11-14 |  |  | 46
| City - Review and Execution of Parking Agreement Amendment No. 2 | 2010-11-14 | 2010-11-21 |  |  | 7
| DDA - Execution of Parking Agreement Amendment No .2 | 2010-11-14 | 2010-11-21 |  |  | 7
| Developer - Review and Execution of Parking Agreement Amendment No. 2 | 2010-11-14 | 2010-11-21 |  |  | 7
PUD, Site Plan and Development Agreement
Council Approval of PUD, site plan and
| Development Agreement | Completed December 1, 2008
Execution of Development Agreement simultaneous with execution of Purchase Agreement-See below
Subdivision and Condominium Documentation
| Submit 95% complete draft Subdivision Plan to City | 2010-12-15 | 2010-12-15 |  |  | 0
| Deposit $40k legal retainer to City | 2010-12-15 | 2010-12-15 |  |  | 0
| Comments on draft of Subdivision Plan from City | 2010-12-15 | 2011-01-05 |  |  | 21
| Submit Final Subdivision Plan to City | 2011-01-05 | 2011-01-19 |  |  | 14
| Draft Master Deed and Condo By-Laws Prepared by City | 2011-01-19 | 2011-02-23 |  |  | 35
| Documents reviewed/completed by Developer and City | 2011-02-23 | 2011-03-25 |  |  | 30
| City Council Approval of Subdivision and Condo Docs | 2011-03-25 | 2011-04-29 |  |  | 35
Affordable Housing Covenant
| Draft covenant prepared by City's attorney | 2011-01-19 | 2011-02-23 |  |  | 35
| Document reviewed/completed by Developer and City | 2011-02-23 | 2011-03-25 |  |  | 30
| City Council Approval of Covenant | 2011-03-25 | 2011-04-29 |  |  | 35
DDA Incentives
| Delineate incentives that Developer will use |  | 2010-09-30
Financing Approvals
| Equity Partner Initial Letter of Interest | Completed 6/1/2010
| Equity Partner Due Diligence Review | 2010-07-01 | 2010-11-30 |  |  | 152
| Executed Term Sheet with Equity Partner | 2010-09-01 | 2010-09-30 |  |  | 29
| Equity Partner Final Committee Approval Process | 2010-12-01 | 2011-01-30 |  |  | 60
| Equity Partnership Documents/Closing | 2010-12-01 | 2011-04-19 |  |  | 139
| Construction Loan Term Sheet Review | 2010-05-24 | 2010-08-30 |  |  | 98
| Signed Term Sheet with Construction Lender | 2010-09-01 | 2010-09-30 |  |  | 29
| Construction Lender Due Diligence | 2010-07-01 | 2010-11-30 | Note: VG to provide list to City of items |  | 152
| Construction Loan Documents | 2010-12-01 | 2011-04-19 |  |  | 139
| Construction Loan Final Committee Approval Process | 2011-02-18 | 2011-04-19 |  |  | 60
| Construction Loan Closing | 2011-04-19 | 2011-06-01 |  |  | 43
Purchase Agreement
| Draft Purchase Agreement prepared by City's attorney | 2011-02-21 | 2011-02-28 |  |  | 7
| Document reviewed/completed by Developer and City | 2011-02-28 | 2011-03-14 |  |  | 14
| City Council Approval of Purchase Agreement | 2011-03-14 | 2011-04-18 |  |  | 35
Purchase of Land
| Price Negotiations for land btw.City and Developer | Completed in 2007
| City - Update due diligence; survey, title, et al | 2011-03-18 | 2011-06-01 |  |  | 75
| Developer - Notice of Execution of Option Agreement | 2011-02-21 | 2011-02-21 | Simultaneous with Construction Loan Closing |  | 0
| Developer & City - Execute Purchase Agreement | 2011-04-18 | 2011-04-25 |  |  | 7
| Developer & City - Schedule Date of Closing | 2011-05-18 | 2011-05-18 |  |  | 0
| Developer & City - Review Closing Statement and Supporting Documents | 2011-05-18 | 2011-05-25 |  |  | 7
Developer - Provides Wire Instructions City & Title Company
| City - Execute Closing Documents | 2011-05-25 | 2011-06-01 |  |  | 7
Developer & City - Closing
| Developer - Execute Development Agreement | 2011-06-01 | 2011-06-01 | Simultaneous with Construction Loan Closing |  | 0
| Record Affordable Housing Covenant | 2011-06-01 | 2011-06-01 |  |  | 0
| Record Master Deed & By-laws | 2011-06-01 | 2011-06-01 |  |  | 0
| Record Deed, Development Agreement, et. al. | 2011-06-01 | 2011-06-01 |  |  | 0
City Bond Issuance
| Resolution of Intent to Issue Bonds (R-08-1090) | Completed 12/15/08
| Resolution Authorizing Issuance of Bonds (R-08-1111) | Completed 12/15/08
Modification of Resolution Authorizing Issuance of Bonds
| City Preparation of Proposed Resolution | 2010-08-23 | 2010-08-30 |  |  | 7
| City Council Approval | 2010-08-30 | 2010-10-04 |  |  | 35
| Sale of Bonds and Closing | 2011-02-18 | 2011-04-19 |  |  | 60
Architectural and Engineering Design
| Schematic Design Approval | Completed 5/2009
| Schematic Design Cost Estimate | Completed 7/2009
| Design Development Document Prep | 2010-08-15 | 2010-10-15 |  |  | 61
| Design Development Owner/GC Review | 2010-10-15 | 2010-11-15 |  |  | 31
| DDA Review and Approval of Design Development Drawings | 2010-10-15 | 2010-11-29 |  |  | 45
| Development Desgn Class 2 estimate Sub Bids | 2010-11-15 | 2010-12-15 |  |  | 30
Construction Documents
| Construction Documents Preparation | 2010-12-15 | 2011-01-22 |  |  | 38
| Construction Documents Value Engineering Meetings | 2011-01-22 | 2011-02-15 |  |  | 24
| Construction Documents 100% Complete/ Submit to City | 2011-02-15 | 2011-03-03 |  |  | 16
Staging Plan
| Submit Preliminary Staging Plan | Completed 6/28/2010
| Submit Updated Staging Plan for Garage Construction | 2011-03-03 | 2011-03-03
| Submit Updated Staging Plan for Residential Bldg. Construction | 2011-03-03 | 2011-03-03
| Building Official Review & Sign-off on Staging Plans | 2011-03-03 | 2011-03-10 |  |  | 7
Civil Construction Plan Review
| Developer delivers civil construction plans to City | 2011-03-03 |  |  |  | 0 | (This will be concurrent with Building Permits but may require 3 plan checks
| Plan Check Review and Comments by City | 2011-03-03 | 2011-03-31 |  |  | 28
| Devleoper Reviews Comments and Resubmit to City | 2011-03-31 | 2011-04-12 |  |  | 12
| 2nd Plan Check | 2011-04-12 | 2011-05-03 |  |  | 21
| Devleoper Reviews Comments and Resubmit to City | 2011-05-03 | 2011-05-10 |  |  | 7
| 3rd Plan Check | 2011-05-10 | 2011-05-31 |  |  | 21
| Approval of civil construction plans | 2011-05-31 | 2011-06-01 |  |  | 1
Building Permits
| Developer delivers contruction plans and building permit app to City | 2011-03-03 | 2011-03-03 |  |  | 0 | [Should be consistent with Construction document section]
| Plan Check Review and Comments by City | 2011-03-03 | 2011-03-24 |  |  | 21
| Review by DDA Engineers | 2011-03-03 | 2011-03-24 |  |  | 21
| Devleoper Reviews Comments and Resubmit to City | 2011-03-24 | 2011-04-12 |  |  | 19
| 2nd Plan Check | 2011-04-12 | 2011-04-26 |  |  | 14
| City Review & Approval of Insurance Certificates/Endorsements and Bonds | 2011-04-12 | 2011-04-26 |  |  | 14
| Grading Permit Issuance | 2011-06-01 | 2011-06-08 |  |  | 7 | [must start after ownership transfers on 6/1/11]
| Building Permt Issuance | 2011-06-01 | 2011-06-08 |  |  | 7
DDA Parking Operating Agreement |  |  |  | need confirmation from DDA
| Draft of document prepared by City and/or DDA | 2011-01-26 | 2011-03-11 |  |  | 45
| Developer Review of Draft Operating Agreement | 2011-03-11 | 2011-03-25 |  |  | 14
| City and DDA Attorney Respond to Developer Comments/ Proposes Edits | 2011-03-25 | 2011-04-08 |  |  | 14
| DDA Operations Committee Review of Operating Agreement | 2011-03-17 | 2011-03-17 |  |  | 0
| Developer/City/DDA Attorney Document Response Edits Completed | 2011-03-17 | 2011-04-01 |  |  | 17
| DDA Board Reviews Draft Operating Agreement | 2011-04-06 | 2011-04-06 |  |  | 0
| Developer/City/DDA Attorney Document Review/Completed | 2011-04-06 | 2011-04-21 |  |  | 15
| DDA Puts Forward Recommended Operating Agreement for Board Approval | 2011-04-27 | 2011-04-27 |  |  | 0
| DDA Votes to Approve Operating Agreement | 2011-05-04 | 2011-05-04 |  |  | 8
| Operating Agreement Executed by Parties | 2011-05-04 | 2011-05-11 |  |  | 7
Construction Commencement
| Mobilization | 2011-06-08 | 2011-06-29 |  |  | 21
| Ground Breaking |  | 2011-06-29
Parking Garage
| Begin/Complete Construction | 2011-06-29 | 2012-05-30 |  |  | 336
| Execute Warranty Bill of Sale to City | 2012-05-30 | 2012-06-06 |  |  | 7
Residential/Apartment Units
| Begin/Complete Construction | 2012-01-05 | 2012-12-31 |  |  | 361
Formulas:
Complete Date = +[Start Date]+[Duration]
Complete Date = [Start Date]+[Duration]
Start Date = +[Complete Date, row above]
Start Date = [Complete Date, row above]